## Sheet1
PBS
| HW | SW | Process | Mobile App | Training
| Server | Google Maps | APP Users | Creating/Setting Account | New SW technologies used
|  | Any SW tools needed | Shop Employee | Detecting location
|  |  | Shop Employer | Adding/removing offers
Previewing offers
WBS
| HW | SW | Training | Mobile App
| Secure server | Installing SW tools needed | Scheduling training for new technologies | Creating/Setting Account | Designing,Developing,Testing
|  |  |  | Detecting location | Designing,Developing,Testing
|  |  |  | Adding/removing offers | Designing,Developing,Testing
|  |  |  | Previewing offers | Designing,Developing,Testing
OBS
PM
| Training Team | Suppliers Manager | Development team | Testing team | Technical writing team
| Trainer1 | Supplier1 | Team leader | Testing Leader | Technical writer1
| Trainer2 | Supplier2 | Developer1 | Tester1 | Technical writer2
| Trainer3 |  | Developer2 | Tester2
|  |  | Developer3 | Tester3