## Sheet1
Assumptions:
1- Each engineer works 8hr/day, 5days/week
2- Total working hours for engineer/month = 8*5 *4 = 160 ≈ 150 hr/month
2- project deadline = 10,000/(150*5) = 13.3333 ≈ 15 months
Questions: | Answers:
Is project delayed? If yes, then by how many days? | No, 500 Hrs ahead
Is project over-budget? If yes, then by how many Hrs? | yes, 1500 Hrs
Ploting:
|  | Planned Value | Actual Cost | Earned value
| 0 | 0 | 0 | 0
| 7.5 | 5000 | 7000 | 5500