## Sheet1
Risks | Probability | Impact | Planing | Action
Server Down | M | H | Mitigate | providing Technical support engineers
Server Hacking | L | H | Mitigate | providing Security engineers
Development/Testing Delaying | M | H | Avoid | Providing enough developers
Training not enough | M | M | Mitigate | Providing reserve time